Project Budget

- Before any project, a crucial step in the lifecycle is to determine a budget
  - Not specific to software industry
  - Once budget is complete, difficult to veer away from it
- Budgets be categorized into 3 cost components
  - Kickoff and Selection
  - Implementation
  - Post-Implementation

- Internal Staff Costs
  - Project leads
  - Developers, Consultants
  - HR
- Travel and Expenses
  - Depending on the size of the project/company, travel may be required
  - Needs to be discussed into the budget
  - Discuss with hardware/software vendors
  - Meet with remote employees/staff
- Include staff out of pocket expenses, lodging and meals
  - Usually staff receives a “per diem” while on travel

Figure 6-1

Project Kickoff and Selection cont.
- Software Costs
  - Any special tools required to assist in the development of the budget
- Legal Counsel
  - Every project small or large, has/should legal cost
  - Contracts
  - Patent/Trademark
  - Intellectual Property (*)
  - License agreements

Project Implementation

- Software/Hardware Costs
  - IDEs, Operating Systems, Database Systems
  - Servers, PC’s, peripheral, memory
  - Network infrastructure, racks, switches
- Training Costs
  - Covers cost of training staff on new tools used during the implementation stage
- Data Costs
  - Migrating, storing data
  - Storage services/devices

- Team Costs
  - Project Team – project manager, team leads
  - User Team – managers, support staff
  - Different budgets for the various roles
- Allocation Overhead
  - Office space and utility expenses
  - Included in budget on case by case basis
- Contingency
  - Monetary allocations to be used in unforeseen situations
  - Some institutions employ this tactic, others do not

Post Implementation
- Maintenance
  - Feature enhancements
  - Bug / security patches
  - Recurring license fees
  - Technical support
  - Disaster recovery

How to Control Costs
- Need to take an “all hands on deck” approach
  - Business analysts
  - Accounting
  - IT executives
- Cooperation is crucial in creating accurate budget
- Conducts research and calculate ROI
  - Hardware
    - Determine solutions
      - Cloud vs In-house Datacenter

- Software
  - Open source vs off the shelf
  - Bespoke vs custom
- Consulting Fees
  - Research the market
    - Determine supply vs demand
    - Buy in bulk?
- Customization Fees
  - Agree to fixed rates
  - Research

Project Scheduling

Software is hard
- Historically, ~ 85% of software projects “fail.” Why?
  - Management sets unrealistic expectations; devs don’t correct them
  - overestimating the positive impact of shiny new tools and hardware
  - hired developers based on availability despite warning signs
  - personality conflicts between developers
  - change in rate structure requirements in middle of work
  - one delay causes another (dev delay leads to test delay)
  - hacks and shortcuts
  - developers end up working death marches
  - overestimating how nearly done you are
  - software written doesn’t match the spec
  - developer time taken away by other tasks
  - tons of bugs come out in testing
  - developer’s don’t listen to testers; ignore severity of bugs reported
  - management breaking promises

- Adding men doesn’t contribute to bringing the work down because we need to account for
  - repartitioning the work
  - traning the new workers
  - increasing intercommunication
- What is Brooks’ suggested schedule?
  - 1/3 for design
  - 1/6 for coding
  - ¼ for unit/component testing
  - ¼ for system testing
- Pro developers often write 50-100 lines of code per day
  - How can it be so low?
  - Does it change based on the programming language used?
- Factors to consider:
  - Should say, 100 lines of correct code per day
  - Are we counting comments? Blank lines? Modified old lines?
- The code must be...
  - designed
  - tested
  - code reviewed
  - checked in
  - maintained / updated
- Productivity
  - Factors that eat up developer time:
    - learning new systems, languages, code
    - documentation
    - testing
    - debugging (getting stuck!)
    - meetings
    - interpersonal communication
    - code reviews
    - design reviews
    - illness
    - real life (family, pets, flat tire, etc.)
    - distraction (Facebook, etc.)

Measuring Productivity
- Ways LoC can be useful:
  - when measured in the same language
  - with the same developer
  - over a long period of time
- Variations
  - Include comments / blank lines in LoC?
- Other ways to measure productivity, besides LoC
  - LoC per month
  - “function points”
  - “eLoc” - substantive lines
  - check-ins
- Why are we so bad at estimating how long a project will take?
- Programmers are optimists “all will go well”
  - programming = creative building with “thought-stuff”
  - therefore, we do not usually imagine that things will go wrong
- We lack practice at measuring how long tasks will take
  - Lose track of time while coding; forget how long it took
  - tend to focus on the time needed to finish “rough” untested code
- We fail to account ahead of time for:
  - bugs; sticking points (sometimes NO progress will be made
  - design / redesign / refactoring
  - testing and debugging (both our code and others’)

Some estimating tips
- Guess how long you think you’ll actually need…
  - Then double (or triple) it.
  - Use a course granularity; days/weeks, not hours.
- Add time to your estimate if:
  - It involves learning any new technologies or systems
  - It involves collaborating with others
  - It is user-facing and therefore needs to be very robust/secure
  - It is concurrent, network-enabled, or lon runing
  - It involves “messy” data or combining data from tmultiple sources

Your project schedules
- Looking back on your intiial estimated project schedules;
  - How accurate were your initial ideas/
    In what way are they the most “off” from what you have actually spent your time doing?
  - Do you know something now that would help you to more effectively schedule a large project in the future? If so, what?